## Practice
Task | Owner | Status | Hours | Project | % complete | Example | Formula result
Kickoff meeting | Priya | Done | 2 | Website relaunch | 0.44444 | Done divided by tasks, without the N/A rows | 0.44444
Requirements doc | Priya | Done | 8 |  |  | Why your percentage is wrong: the bottom line | 4 of 9 tasks done
Wireframes | Tom | Done | 12 |  |  | Weight by hours: percent of the work done | 0.22727
Database setup | Ana | In progress | 16 |  |  | Percent complete per person with COUNTIFS | 0.5
API endpoints | Ana | Not started | 24 |  |  | Add a progress bar | ████░░░░░░ 44%
Front-end build | Tom | In progress | 30
Legacy data import | Ana | N/A | 6
User testing | Priya | Not started | 10
Launch checklist | Tom | done | 3
Training video | Priya |  | 5
Print brochures | Tom | N/A | 4