## Practice
Task | Start | Workdays needed | Deadline | Holidays | As of | 2026-11-04 | Example | Formula result
Copywriting | 2026-11-02 | 5 | 2026-11-06 | 2026-11-26 |  |  | Same plan, two questions | 46335
Print proofs | 2026-11-07 | 3 | 2026-11-11 | 2026-12-25 |  |  | The off-by-one: who counts the start day | 46332
Design review | 2026-11-20 | 5 | 2026-11-30 | 2027-01-01 |  |  | Going backwards: negative days and reversed dates | 46350
Year-end close | 2026-12-21 | 8 | 2027-01-05 |  |  |  | One holiday list for both | 46356
Client report | 2026-11-04 | 12 | 2026-11-20 |  |  |  | Custom weekends: WORKDAY.INTL and NETWORKDAYS.INTL | 46343
Formulas:
Formula result = WORKDAY([Start],[Workdays needed])
Formula result = WORKDAY([Start, row above]-1,[Workdays needed, row above])