## Job cost
Job cost report
Job | Kitchen remodel, job 26-118
Contract price |  | 48500
Approved change orders (billed) |  | 3250
Revised contract |  | 51750
Code | Cost item | Original budget | Change order cost | Revised budget | Actual to date | Est. to complete | Projected final | Over / under | Status
01 | Demo and disposal | 2400 | 0 | 2400 | 2650 | 0 | 2650 | -250 | Over
02 | Framing and blocking | 3100 | 450 | 3550 | 3320 | 200 | 3520 | 30 | OK
03 | Plumbing (sub) | 6800 | 1200 | 8000 | 5900 | 2000 | 7900 | 100 | OK
04 | Electrical (sub) | 5200 | 800 | 6000 | 4100 | 1700 | 5800 | 200 | OK
05 | Drywall and paint | 3400 | 0 | 3400 | 1200 | 2100 | 3300 | 100 | OK
06 | Cabinets | 9800 | 0 | 9800 | 9800 | 0 | 9800 | 0 | OK
07 | Countertops | 4600 | 0 | 4600 | 0 | 4950 | 4950 | -350 | Over
08 | Tile and flooring | 3900 | 0 | 3900 | 600 | 3200 | 3800 | 100 | OK
09 | Supervision and cleanup | 1800 | 0 | 1800 | 950 | 800 | 1750 | 50 | OK
Total |  | 41000 | 2450 | 43450 | 28520 | 14950 | 43470 | -20
Projected cost |  | 43470
Projected profit |  | 8280
Projected margin |  | 16%
Lines over budget |  | 2
Percent complete (cost to date / projected cost) |  | 65.61%