## Risk register
Risk register
Project | Website relaunch
As of | 2026-11-02
ID | Risk | Owner | Likelihood (1-5) | Impact (1-5) | Score | Rating | Next review | Status
R-01 | Client content arrives late | Jon | 4 | 4 | 16 | High | 2026-11-06 | Open
R-02 | Key developer unavailable during build | Luis | 2 | 5 | 10 | Medium | 2026-11-09 | Open
R-03 | Redirects missed, search traffic drops after launch | Jon | 3 | 4 | 12 | Medium | 2026-10-30 | Open
R-04 | Stakeholders request new pages after design sign-off | Maya | 4 | 3 | 12 | Medium | 2026-11-13 | Open
R-05 | Hosting migration needs extra security review | Luis | 2 | 3 | 6 | Low | 2026-11-20 | Open
R-06 | Accessibility issues found late in QA | Maya | 3 | 3 | 9 | Medium | 2026-11-27 | Open
R-07 | Stock photo licences not cleared | Priya | 2 | 2 | 4 | Low | 2026-10-23 | Closed
R-08 | Brand guidelines change mid-project | Priya | 1 | 4 | 4 | Low | 2026-11-30 | Open
R-09 | Analytics tracking breaks on new templates | Luis | 3 | 2 | 6 | Low | 2026-11-25 | Open
Open risks | 8
Open high risks | 1
Open medium risks | 4
Reviews overdue | 1
Risk RAG | Red
Open risks: likelihood (rows) x impact (columns)
| 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 1 | 1 | 0
3 | 0 | 1 | 1 | 1 | 0
2 | 0 | 0 | 1 | 0 | 1
1 | 0 | 0 | 0 | 1 | 0