## Status report
Weekly project status
Project | Website relaunch
Status date | 2026-11-02
Budget | 31920
Spent to date | 17005
Work complete (hours-weighted) | 47%
Holidays | 2026-11-26 | 2026-11-27
Milestone | Baseline date | Forecast date | Done? | Slip (working days) | Status
Requirements signed off | 2026-10-09 | 2026-10-09 | Yes | 0 | Done
Wireframes approved | 2026-10-23 | 2026-10-23 | Yes | 0 | Done
Design sign-off | 2026-10-30 | 2026-11-06 | No | 5 | At risk
Content complete | 2026-10-30 | 2026-11-11 | No | 8 | Slipping
Site build complete | 2026-11-25 | 2026-11-30 | No | 1 | At risk
Launch | 2026-12-08 | 2026-12-10 | No | 2 | At risk
Budget used | 53.27%
Cost performance index (CPI) | 0.88
Forecast cost at completion | 36273
Milestones slipping or missed | 1
Schedule | Red
Budget | Red
Overall | Red
Headline | Overall Red: 1 milestone(s) slipping, 53% of budget used for 47% of the work
Formulas:
Slip (working days) = IF([Baseline date]="","",IF([Forecast date]>[Baseline date],NETWORKDAYS([Baseline date],[Forecast date],B7:C7)-1,-(NETWORKDAYS([Forecast date],[Baseline date],B7:C7)-1)))