## Tasks
Project task tracker
Project | Website relaunch
Status date | 2026-11-02 |  | Due soon = within (days) |  |  | 7
Task | Owner | Start | Due | Done on | Status | % done | Days late | Flag
Kickoff and goals | Maya | 2026-09-01 | 2026-09-05 | 2026-09-04 | Done | 100% | 0 | Done
Content audit | Luis | 2026-09-08 | 2026-09-18 | 2026-09-23 | Done | 100% | 5 | Done late
Sitemap and navigation | Maya | 2026-09-14 | 2026-09-25 | 2026-09-25 | Done | 100% | 0 | Done
Wireframes | Tara | 2026-09-21 | 2026-10-09 | 2026-10-08 | Done | 100% | 0 | Done
Visual design | Tara | 2026-10-05 | 2026-10-23 |  | In progress | 80% | 10 | Overdue
Copywriting: product pages | Luis | 2026-10-05 | 2026-10-30 |  | In progress | 60% | 3 | Overdue
Copywriting: blog migration | Luis | 2026-10-19 | 2026-11-13 |  | Not started | 0% | 0 | Late start
Product photography | Jess | 2026-10-12 | 2026-10-28 | 2026-10-27 | Done | 100% | 0 | Done
CMS setup | Omar | 2026-10-12 | 2026-10-30 | 2026-10-29 | Done | 100% | 0 | Done
Front-end build | Omar | 2026-10-26 | 2026-11-20 |  | In progress | 25% | 0 | On track
Product data import | Omar | 2026-11-02 | 2026-11-06 |  | Not started | 0% | 0 | Due soon
Redirect map (old to new URLs) | Maya | 2026-10-26 | 2026-11-06 |  | Blocked | 30% | 0 | Blocked
Analytics and tracking | Jess | 2026-11-09 | 2026-11-13 |  | Not started | 0% | 0 | On track
QA and browser testing | Tara | 2026-11-16 | 2026-11-25 |  | Not started | 0% | 0 | On track
SEO checks | Maya | 2026-11-16 | 2026-11-24 |  | Not started | 0% | 0 | On track
Launch | Maya | 2026-11-30 | 2026-11-30 |  | Not started | 0% | 0 | On track
Summary |  |  | Owner | Open tasks | Overdue | Days late (total)
Tasks | 16 |  | Maya | 3 | 0 | 0
Done | 6 |  | Luis | 2 | 1 | 8
In progress | 3 |  | Tara | 2 | 1 | 10
Not started | 6 |  | Jess | 1 | 0 | 0
Blocked | 1 |  | Omar | 2 | 0 | 0
Overdue now | 2
Due soon | 1
Overall progress | 49.69%